Hearst Networks: Compliance Process Guide

Stage One: Pre-Production Process

Who Attends:
☑️ Commissioning Editor
☑️ Production Company
☑️ Hearst Compliance Team

Actions (Minimum 3 Weeks Before Filming):
☑️ Arrange a pre-production meeting
☑️ Production Company and Commissioning to send the following information to Compliance:

- Confirmed stories/cases/episode information (allow 3 days for feedback)

- Up-to-date pitch or treatment.

☑️ During the meeting, discuss:

- High-level Compliance advice based on the pitch/treatment

- Procedure for uploading rough/fine cuts and receiving feedback

- Turnaround time for Compliance feedback

☑️ After the meeting, provide:

- Rough and fine cut schedule (required 3 weeks before rough cut submission).

- TX delivery schedule

- Any duty of care/safeguarding protocols and any external legal advice sought (if confirmed as necessary)

Stage Two: Rough and Fine Cut Submissions

Rough Cuts:
☑️ Submit rough cuts to the Commissioning Editor and Compliance for review

Compliance Feedback Timelines:
☑️ Compliance provides feedback within 3 business days
☑️ Production Company responds to Compliance queries within 3 business days
☑️ For feedback requests outside business hours, please discuss in advance with the Director of Compliance

☑️ If legal counsel has been sought, please share the advice with Hearst Compliance along with the cuts.

Fine Cuts:
☑️ Submit fine cuts to the Commissioning Editor and Compliance for review

☑️ Hearst Compliance will verify the final cut. Please ensure all outstanding queries have been addressed before the TXM is delivered. Unresolved issues may cause rejection and delay

Post-Delivery Considerations:
☑️ Discuss plans for press coverage, social media, digital content and duty of care with Compliance post filming

Risk Escalation:

For risk and escalation, please contact the Director of Compliance at Hearst Networks